## Sheet1
Task # | Employee Name & User ID that will complete this task | Module | Task to be Completed | Comments | Navigation | Required or Optional?
Data Validation
1 |  | PO | Compare 8.9 to 9.2 Query BOR_PO_OPEN_AMOUNT_ALL | Data Validation | Files will be downloaded from ITS File Transfer Utility (FTU) site. Access will only be needed if differences found. | Required Sign-Off
2 |  | ePro | Compare 8.9 to 9.2 Query BOR_REQ_OPEN_AMOUNT_ALL | Data Validation |  | Required Sign-Off
3 |  | AP | Compare 8.9 to 9.2 Query BOR_AP_OPEN_LIAB | Data Validation |  | Required Sign-Off
4 |  | Expenses | Compare Query 8.9 BOR_EX_OPEN_LIAB_IN_EX to 9.2 BOR_EX_OPEN_LIAB | Data Validation |  | Required Sign-Off
5 |  | GL | Compare 8.9 to 9.2 Query BOR_TRIAL_BALANCE | Data Validation |  | Required Sign-Off
6 |  | GL | Compare 8.9 to 9.2 Query BOR_GL_LEDGER_BALANCES | Data Validation |  | Required Sign-Off
7 |  | KK | Compare Query 8.9 BOR_KK_ENC_BAL_AS_OF_PD to 9.2 BOR_KK_ENCUMB_AS_OF_PD | Data Validation |  | Required Sign-Off
8 |  | KK | Compare 8.9 to 9.2 Budget Status Report | Data Validation |  | Required Sign-Off
9 |  | AM | Compare Query 8.9 BOR_ASSET_LISTING_AUDITORS to 9.2 BOR_AM_ASSET_LISTING | Data Validation |  | Required Sign-Off
10 |  | AM | Compare 8.9 to 9.2 Federal Asset Report | Data Validation |  | Required Sign-Off
11 |  | Benefit Recon | Run the Benefit Premium Recon Report (BORR025) in 9.2 and compare it with your 8.9 February report saved prior to the upgrade (if report used by your institution). | Data Validation | BOR Menus>BOR Payroll>Benefit Reconciliation>Benefit Accounting>Benefit Inquiry/Reports>Benefit Premium Recon Rpt | Required Sign-Off
12 |  | Benefit Recon | Run the Retiree Receivable Aging Report in 9.2 and compare it with your 8.9 February report saved prior to the upgrade. | Data Validation | BOR Menus>BOR Payroll>Benefit Reconciliation>Retiree Benefit Accounting>Retiree Benefit Inquiry/Rpts>Retiree Receivalbe Aging | Required Sign-Off
13 |  | Benefit Recon | Run the Open Coupon Query in 9.2 and compare it with your 8.9 February report saved prior to the upgrade. | Data Validation | BOR Menus>BOR Payroll>Benefit Reconciliation>Benefit Accounting Audit Tools>Open Coupon Query | Required Sign-Off
14 |  | Common Remitter | Run the Retiree Provider Summary History Report in 9.2 and compare it with your 8.9 February report saved prior to the upgrade. | Data Validation | BOR Menus>BOR Payroll>Common Remitter>Retirement>Retirement Inquiry>Ret Provider Summary Hist | Required Sign-Off
15 |  | Common Remitter | Run the TSA Remittance Summary Report in 9.2 and compare it with your 8.9 report for Payrun ID 235. | Data Validation | BOR Menus>BOR Payroll>Common Remitter>TSA>TSA Inquiry>TSA Remittance | Required Sign-Off
16 |  | ALL | Institutions that have Consolidated - confirm you still have access to the historical data in your previous Business Units | (Augusta State, North Georgia, Gainesville State, Macon State, Middle Georgia, South Georgia, Waycross, Skidaway) | N/A | Required Sign-Off
Cutover and Validation Tasks
17 |  | Expenses & GFM | Validate Access to Employee Self-Service | Expenses and GFM |  | Required Sign-Off
18 |  | Security | Validate Security Changes made in FPRE UAT database exist | Refer to list of Users provided to ITS with changes made in FPRE |  | Required Sign-Off
19 | N/A - this will apply to all users | Security | Confirm appropriate access to pages for performing your normal job functions | In the event you do not have access to expected pages, contact your Security Administrator | Varies by user | N/A since local Security Admins will resolve these.
20 |  | Security | Confirm appropriate Query Security Access (Query Manager or Viewer) | Should have the same access as 8.9. Note: BI Publisher reports require Query Manager access in 9.2. | Reporting Tools>Query | Required Sign-Off
21 |  | All | Validate that Institutional queries exist. If changes to queries were made in FPRE UAT, confirm the changes exist. |  | Reporting Tools>Query | Required Sign-Off
22 |  | All | Make query changes made in 8.9 production if not completed in FPRE during UAT or made after 2/25/2015. | Production Query & Tree freeze date - 1/09/2015. FRE UAT taken down as of 2/25/2015. | Reporting Tools>Query | Optional
23 |  | GL/KK | Validate GL WorkCenter | If you do not have access, contact your Security Admin and confirm you have been assigned BOR_GL_WORKCENTER, BOR_GL_DASHBOARD, BOR_WORKCENTER_USER roles. | General Ledger> WorkCenter | Optional
24 |  | GL/KK | Validate institution trees exist. If production changes were made in FPRE UAT database, confirm changes exist. |  | Tree Manager | Required Sign-Off
25 |  | GL/KK | Make tree changes made in 8.9 production if not completed in FPRE during UAT or made in production after 2/25/2015. |  | Tree Manager | Required Sign-Off
26 |  | AP | Upload Production AP Signature Image file (.png) |  | BOR Menus>BOR Accounts Payable>BOR AP Use and Processing>AP Check Image Upload | Required Sign-Off
27 |  | AP/Banking | Validate Banking information mapped correctly to different 9.2 fields. Make updates as needed. | If you had to make changes (e.g. bank or institution name in all CAPS) as requested by your bank during UAT, you will need to make those changes in production. | 1. BOR Menus>BOR Utilities>BOR EFT Formatting | Required Sign-Off
28 |  |  |  |  | 2. Banking>Bank Accounts>External Accounts | Required Sign-Off
29 |  |  |  |  | 3. Banking>Banks and Brancesh>Bank Branch Information | Required Sign-Off
30 |  |  |  |  | 4. Banking>Banks and Branches>Bank Information | Required Sign-Off
31 |  |  |  |  | 5. Set Up Financials/Supply Chain>Common Definitions>Location>Location | Required Sign-Off
32 |  |  |  |  | 6. Set Up Financials/Supply Chain>Business Unit Related>Payables>Payables Definition | Required Sign-Off
33 |  | AP/Suppliers | New ACH Payment Notifications - Validate email addresses in Supplier | ITS is copying remit address Emails to new Payment Notification Email ID field. Review and update as needed. | Suppliers>Supplier Information>Add/Update>Supplier>Location tab, Payables link, Payment Notification | Optional
34 |  | AP/Security | New ACH Payment Notifications - Have Security Admin populate the from email account to be used for emailing the payment advices to supplier. |  | Set Up Financials/Supply Chain > Common Definitions > User Preferences > Define User Preferences | Optional
35 |  | AP | New ACH Payment Notifications - Update ACH pay cycle to select checkbox to enable Email Payment Advice. |  | Accounts Payable>Payments>Pay Cycle Processing>Payment Selection Criteria | Optional
36 |  | AP | Validate Positive Payment Format Transmittal Code | New format available in 9.2 for Synovus Bank needs to be selected by Darton and Albany State at go-live. | BOR Menus>BOR Utilities>Installation Options | Required Sign-Off
37 |  | AP | Validate AP WorkCenter | If you do not have access, contact your Security Admin and confirm you have been assigned BOR_AP_WORKCENTER, BOR_AP_DASHBOARD and BOR_WORKCENTER_USER roles. | Accounts Payable>WorkCenter | Optional
38 |  | ePro/GFM | Institutions using GeorgiaFIRST Marketplace - Punch out from ePro Requistion to GFM |  | eProcurement>Requisition | Required Sign-Off
39 |  | Expenses | View expense profile of a recent hire. Verify they are present and information is accurate |  | Travel and Expenses > Manage Employee Information > Update Profile | Required Sign-Off