## Sheet1
Institution Name: |  | Any Campus | [15 empty] | July - September
Report Submitted By: |  | Contact Person | [15 empty] | October - December
Contact Email Address: |  | contact person@campus.com | [15 empty] | January - March
Date: |  | 2016-01-15 | [15 empty] | April - June
Project |  |  |  | Status | Budget |  | Design |  |  |  |  | Construction |  |  |  |  | Construction Costs |  | Comments
Number | Name |  | Delivery Method | Phase | Total | SCL | Design Professional | Indicate Prime Ownership Status (MBE/WBE) | MBE Team Participation (%) | WBE Team Participation (%) | Contract Date | Bid Date | Contruction Professional | % Complete | NTP Date | Material Completion Date | Original Contract Amt./GMP | Current Contract Amt.
BR-00-0000 | Renovation of the North Campus Complex |  | DBB | C | 45000000 | 38000000 | ABC Architectural Firm | Other | 15 | 15 | 2015-11-15 | 2015-10-30 | DEF Construction Company | 10 | 2015-11-15 | 2016-12-15 | 37000000 | 37000000