## Issues Tracking
Issue No. | Action Item | Status | Priority | Description | Assigned To | Resolution/ Comments | Reported By | Date Reported | Date Assigned | Aged Until Closed | Date Closed
Budget Prep - Functional Issues
BP1.0 | Job Code not Updating | Open | Med | When updating job code the position name does not change. | IT/Christy Todd |  | GPC/Jaimie | 2013-05-13 | 2013-05-15
BP2.0 | FTE/Position counts -reporting inconsistencies | Open | Medium | Inconsistency in how positions should be counted. Multiple reports that are not consistent in how the count is to be determined. | IT/Christy Todd & OFA/Tracie Dixon | Need to define methodology based on source and need of information so that institutions can be consistent in reporting. | GPC/Jaimie | 2013-05-13 | 2013-05-15
BP5.0 | Tables not updating in a timely manner | Open | High | BOR_BUDAGG was not updating the last few days prior to budget due date. | IT/Christy Todd | Update nightly | Team | 2013-05-13 | 2013-05-15
BP10.0 | Personal Services Online Updates does not allow user to enter full 10 digit ADP deptid. | Open | Med | Field truncates at 7 digits and user must then use drop down menu to identify deptid. | IT/Christy Todd | Extend field | Team | 2013-05-13 | 2013-05-15
BP12.0 | Fringe Benefits on Schedules E and E-1 not agreeing. | Open | Med | Schedules do not agree for Auxliary fund; fund group 12220 not picked up on Schedule E-1 | IT/Christy Todd |  | Columbus/Melanie | 2013-05-13 | 2013-05-15
Budget Prep - Enhancements
BP3.0 | Ability to update mulitiple positions when change in ADP code | Open | Medium | Ability to make mass changes when changing ADP code for many positions | IT/Christy Todd |  | GPC/Jaimie | 2013-05-13 | 2013-05-15
BP4.0 | Ability to remove $0 budget lines prior to loading budget and have lines removed from schedules. | Open | Medium | Ability to choose and remove $0 budget lines prior to creating journal load to Financials. | IT/Christy Todd | Add option on panel to remove line (safegaurd to allow only $0 lines) | GPC/Jaimie | 2013-05-13 | 2013-05-15
BP6.0 | Grant Budget Inquire screen- ability to view by department id | Open | Medium | Currently this screen only allows user to pul by project id. Would like option to pull also by department id | IT/Christy Todd |  | GPC/Jaimie | 2013-05-13 | 2013-05-15
BP7.0 | Budget Prep changes when converting to higher version of PeopleSoft | Open | High | Need to know what changes will be made to Budget Prep in new version | Tracey Cook | Involvement in discussions | Team | 2013-05-13 | 2013-05-15
BP8.0 | Addition of audit trail to track changes | Open | Med | Difficult to determine what changes have been made and by whom; would like ability to track all changes | IT/Christy Todd |  | Valdosta/Jan | 2013-05-13 | 2013-05-15
BP9.0 | USG On line system - automatic population of institution information when logging in. | Open | Low | Currently have to log in and then choose institution. | OFA/Tracie Dixon |  | GA Tech/Steve | 2013-05-13 | 2013-05-15
BP9.1 | USG On line system - consolidated schedule for institutions with "B" units | Open | Low | Currently have to run both schedules and manually total. | OFA/Tracie Dixon |  | GA Tech/Steve | 2013-05-13 | 2013-05-15
BP11.0 | Mass Updates - ability to add a range of fund groups | Open | Low | Ability to make mass updates for a range of funds instead of a single fund. | IT/Christy Todd |  | Team | 2013-05-13 | 2013-05-15

## Archive
Issue No. | Action Item | Status | Priority | Release | Description | Assigned To | Resolution | Reported By | Date Reported | Date Assigned | Date Needed | Aged Until Closed | Date Closed